## Slide 1
HAIR MNL
Engineering Brief
Replacing Stky
Sticky Add-to-Cart
Feasibility & Recommendation
HairMNL Engineering · May 2026

## Slide 2
What Stky Does Today — and How It's Wired In
2 / 9
$6.99 – $18.99
per month
Assumed: $11.99/mo
(Grow plan — unlimited)
STKY by Codeinero
“Built for Shopify” · 4.9★
~₱660–₱1,050/mo
+ ~600ms Azure CDN
Stky provides two features the theme uses today:
PDP sticky add-to-cart bar (variant + qty + CTA, follows scroll)
Collection-page Quick Buy overlay (.satcb_quick_buy on product cards)
Integration footprint in this repo:
config/settings_data.json — App block registration (correct Shopify App Embed)
layout/theme.liquid:89 — DNS prefetch hint for satcb.azureedge.net
assets/theme.css:15678 — z-index override for the Quick Buy overlay
layout/theme.liquid:969 — second, hardcoded <script> tag (more on next slide)

## Slide 3
The Integration Has Already Drifted
3 / 9
⚠ Two issues already exist that need fixing — replacement or not.
Issue 1 — Hardcoded script with the wrong shop parameter
layout/theme.liquid:969 contains a hardcoded <script src="…/satcb.min.js?shop=creations-gdc.myshopify.com"> — a leftover from when this theme was forked from another store. It loads on every page in parallel with the legitimate Shopify App Embed, doubling the third-party script cost and potentially mis-attributing analytics. Should be removed regardless of whether Stky stays.
Issue 2 — DNS-prefetch comment misidentifies the domain
layout/theme.liquid:78 comments satcb.azureedge.net as “Same-day store pickup widget, ~600 ms” — but the domain serves Stky's Sticky Add to Cart Bar. Mislabel suggests the original installer didn't know what the script did. Documentation hygiene + a signal that the integration was poorly understood from day one.

## Slide 4
Proposed Architecture: Theme-Native, No Backend
4 / 9
1
Liquid snippet
snippets/sticky-add-to-cart.liquid
Markup for the bottom-fixed bar: product image, title, price, variant selector, qty, Add to Cart button.
Rendered once in layout/theme.liquid; hidden by default, shown on scroll.
2
JS module
assets/sticky-atc.dev.js + .js
IntersectionObserver on the primary product form. When the original ATC button scrolls out of view, the sticky bar becomes visible. Submits via the existing cart drawer flow.
~150 LoC. No new dependencies.
3
CSS additions
snippets/css-overrides.liquid
Brand-styled bar: position: fixed, z-index, mobile breakpoint, transition. Reuses existing CSS tokens for colors and typography.
kt0-safe — no containing-block traps on parent elements.
✔ No backend service. No third-party CDN. Code lives in this repo and ships with the theme.
✔ Re-uses theme's existing variant selector + Add-to-Cart flow + cart drawer — no parallel state.
✔ Eliminates ~600ms Azure latency, the duplicate script tag, and the stale shop parameter.

## Slide 5
12-Month Cost · Payback in Month 1
5 / 9
Scenario | Monthly Cost | Annual Cost | 3-Year TCO
Status quo — Stky Basic ($6.99/mo) | $6.99 | $83.88 | ~$252
Status quo — Stky Grow ($11.99/mo, assumed) | $11.99 | $143.88 | ~$432
Theme-native replacement | $0 | $0 | $0
Engineering effort: ~4–6h serial work (1–2 calendar days). At the assumed Grow tier, replacement pays back its engineering cost within 4–8 weeks, then is pure savings. Bonus: the duplicate-script bug at theme.liquid:969 needs cleanup anyway — replacement absorbs that work for free.

## Slide 6
What We Recreate · What We Drop
6 / 9
Stky Feature | Recommendation | Rationale
PDP sticky add-to-cart bar | Recreate | Core feature; visible to every shopper on every PDP scroll. Brand-styled, mobile-responsive, ~150 LoC JS module.
Collection-page Quick Buy | Stakeholder ask | Already in use (z-index override exists). Adds modal-open complexity. See slide 8 — recommend dropping for v1, revisit if conversion data justifies.
Slider cart drawer / upsell | Drop | Theme already has its own cart drawer. Stky's version is unused or duplicative.
Countdown urgency timer | Drop | Not visible to verify in current theme; aggressive UX pattern; minimal proven lift. Drop unless data justifies.
Floating cart icon | Drop | Theme header cart icon already serves this purpose.

## Slide 7
Timeline (1–2 Days) and Known Risks
7 / 9
Build phases
T1 · Liquid snippet ~30 min
T2 · JS module (dev + min) ~2h
T3 · CSS + kt0 lint guard ~1h
T4 · (optional) Quick Buy overlay ~1h
T5 · Draft-theme smoke test ~45 min
T6 · Cutover — disable Stky embed, remove stale script + DNS prefetch + CSS override ~30 min
Known risks
PDP conversion dips post-cutover
Draft-theme A/B for 48h before publishing; rollback = re-enable Stky App Embed in one click.
Mobile bar overlaps fixed footer
Verify against bottom nav/safe-area-inset-bottom in smoke test (T5).
kt0 containing-block trap on .sticky-atc-bar
Lint guard added in T3; same pattern proven in BIS work.
Variant selector state drift between bar and primary form
Single source of truth — bar reads from primary form's variant input via event listeners.

## Slide 8
Three Decisions Needed
8 / 9
01
Proceed?
Approved to replace Stky with a theme-native implementation?
1–2 days engineering. Pays back in ~4–8 weeks at $11.99/mo; pure savings after. Cleans up two pre-existing integration bugs.
Engineering recommends: yes
02
Quick Buy Overlay?
Recreate the collection-page Quick Buy button, or drop?
Drop = 1 fewer ticket + simpler PDP funnel. Keep = parity with current site behavior, +1h engineering. Conversion impact unknown.
Engineering recommends: drop for v1
03
Plan Verification
Confirm which Stky plan HairMNL is on today.
Annual cost depends on plan: Basic ($83.88), Grow ($143.88), or Advanced ($227.88). Cost-comparison slide assumes Grow.
Brand owner: please confirm in Stky billing

## Slide 9
Appendix — Engineering Detail
9 / 9
A — Files at cutover
NEW: snippets/sticky-add-to-cart.liquid, assets/sticky-atc.dev.js, assets/sticky-atc.js
DELETE: layout/theme.liquid:969 (hardcoded script with wrong shop param)
MODIFIED: layout/theme.liquid (render snippet + remove DNS prefetch comment), snippets/css-overrides.liquid (sticky bar styles), assets/theme.css (remove .satcb_quick_buy override), config/settings_data.json (disable Stky app block), scripts/check-overlay-css.py (add .sticky-atc-bar to OVERLAY_PATTERNS)
B — Engineering ticket graph
Epic: Replace Stky Sticky Add-to-Cart with theme-native implementation
T0 this deck (CC) → T1 Liquid snippet (OC) → T2 JS module (OC) → T3 CSS + kt0 lint (OC) → T4 Quick Buy overlay [conditional] (OC) →
T5 Smoke test (CC) → T6 Cutover (CC)
C — Source: Stky on the Shopify App Store
apps.shopify.com/sticky-add-to-cart-bar · Developer: Codeinero · 4.9★ (467 reviews) · Pricing verified May 2026