## Slide 1
HairMNL.com
Theme Modernization
Progress, Roadmap & Decisions Pending
Founders · Marketing · Web team
May 14, 2026

## Slide 2
Where we are — one-page read
Mobile blocking time
+25.8 pp
Desktop CLS p75 good 30.5% → 56.3% (May 6 → May 14)
Desktop blocking time
+7.8 pp
Mobile CLS p75 good 74.5% → 82.3% (May 6 → May 14)
Code-health debt
−97.9%
Theme-check linter 1,554 → 33 offenses (May 2)
Annual cost saved + in flight
~$5,400
Locked $2,388 (AMP +) · in-flight $3,000–4,200 (Vertex)
What changed since the last roadmap (Apr 29)
CLS sprint — 8 fixes shipped (Apr 29 → May 2)
GTM cleanup v140 — 28 pixel tags removed, bot exclusion live
CWV dashboard live on GitHub Pages (Apr 29 → May 1)
Theme-check linter pass: 1,554 → 33 (May 2)
Vertex AI build PR-1 → PR-6 shipped on draft
Critical CSS audit (ax0) — 3 dupe rules removed; 363 bytes saved (May 3)
Snippet DRY-up (aoe) — branded product card −193 lines; 25+ callers unchanged (May 3)
Shop Sheriff AMP fully uninstalled — savings captured
What needs founder sign-off this week
(1) LimeSpot 4 admin tweaks — free, ~2–5% AOV uplift
(2) Vertex AI cutover plan approval (in principle)
(3) Admin batch — URL Redirect + Judge.me Lite
(4) BSS B2B Customer Portal full uninstall (founder-only)
(5) Dual sale-label decision — parked to Jun 1

## Slide 3
Performance dashboard
Lab is noisy; CrUX field (28-day rolling) is ground truth
Metric | Apr 26 baseline | Apr 27 best | May 2 (post-9g9) | May 3 (n=4) | CrUX field URL
Mobile LCP | 11.8 s | 6.3 s | 9.17 s | ~14.2 s | 3.54 s ✓ AVG
Mobile TBT | 4,340 ms | 1,530 ms | 5,010 ms | ~4,155 ms ✓ | — (INP 277 ms)
Mobile CLS | 0.043 ✓ | 0.047 ✓ | 0.041 ✓ | 0.035 ✓ | 0.30 POOR
Desktop TBT | 5,600 ms | 774 ms | — | 2,340 ms ✓ | 132 ms FAST ✓
Desktop LCP | 1.5 s | — | 1.33 s ✓ | — | 2.38 s FAST ✓
Read
TBT trend is healthy. Yesterday's 5,010 ms median was noise — today's n=4 settles to ~4,155 ms. The May 2 BSS render fix did not regress TBT.Mobile lab LCP is throttling artifact. Slow-4G + Moto G Power amplifies banner image weight. CrUX field LCP shows real shoppers at 3.54 s (AVG) on desktop and improving on mobile — Phase 1 wins won't fully surface in the 28-day field window until ~May 26.Field CLS p75 = 0.30 is the dominant remaining problem. 8 fixes shipped Apr 29 → May 2. Validation re-query May 9.

## Slide 4
Before / after — Apr 26 baseline → May 3
Cumulative impact of Phase 1 sprint
BEFORE — Apr 26
Mobile Lighthouse score 26
Mobile TBT 4,340 ms
Desktop TBT 5,600 ms
Field CLS 0.30 (POOR)
38 third-party tracking pixels in GTM
Lazysizes + Hotjar + Booster live
Critical CSS 70 KB inline
theme.css 448 KB
1,554 theme-check offenses
AMP serving 19 clicks / month for $99/month
Klaviyo popup hijacking LCP
GA4 contaminated by 538k bot events / 14d
AFTER — May 3
Mobile Lighthouse score 27 → 39 window
Mobile TBT ~4,155 ms (lab); CrUX INP 277 ms
Desktop TBT 774 ms · field 132 ms FAST
Field CLS — 8 fixes shipped, May 9 re-query
10 pixel tags in GTM (28 deleted)
Native loading="lazy"; Hotjar + Booster gone
Critical CSS 39 KB inline (−44%)
theme.css 350 KB (−22%) + 4 deferred bundles
33 theme-check offenses (−97.9%)
AMP uninstalled — savings $1,188/yr captured
Popup deferred 20 sec + 60% scroll
Bot exclusion v139 live; clean attribution

## Slide 5
What we shipped — JavaScript reduction
Phase 1 sprint, Apr 26 → May 3
Lazysizes library removed — replaced with native loading="lazy" (~30 KB JS + IO-shim cost)
BSS B2B portal scripts gated to backbar-approved customers only (~185 KB saved per guest pageload)
LimeSpot SDK deferred (was render-blocking)
Klaviyo popup deferred (20 sec + 60% scroll trigger)
Searchanise + Hotjar + Booster Page Speed Optimizer removed
Animated hero fade-in disabled (CLS); mega-menu staggered fade disabled (INP)
jQuery + aio_stats deferred
storepickup.js deferred + gated to product/cart templates only
bss-hide-variant.css + tiny.content.min.css deferred
Below-fold homepage Swipers + cross-post-blogs Swiper lazy-init via IntersectionObserver
node-html-parser replaced with native textContent (runtime + bundle win)
Homepage blog-card layout pass deferred to first-scroll

## Slide 6
What we shipped — CSS architecture
Smaller payloads, single recalc, better cache
Critical CSS trimmed 70 KB → 39 KB inline (−44%)
Four rounds of CSS extraction from theme.css: 448 KB → 350 KB (−22%)
Per-template CSS gating (account, blog, search, password)
Four deferred CSS files bundled into deferred-extras.css — single recalc event saved −2,850 ms TBT
Switched preload pattern to media=print swap for 5 split bundles
Self-hosted Playfair Display fonts (Latin + Latin-ext woff2)
Inlined font-settings CSS
Critical CSS audit + regen (ax0, May 3) — penthouse run across 6 templates confirmed 39 KB is well-tuned; 3 duplicate rules removed + btn--outline property deduped; 363 bytes saved; shipped to live
Snippet DRY-up (aoe, May 3) — product-grid-item-branded + subcollection merged into one file (−193 lines, 4-line stub); all 25+ callers unchanged

## Slide 7
What we shipped — image / LCP
Hero + responsive + WebP + width/height everywhere
Mobile/desktop hero split via <picture> + <source media>
Hero preload + fetchpriority="high" on first slide only — extended to collection-hero
Banner preload URL aligned to WebP source — eliminated 2,581 ms resource-load delay
Responsive srcset on product thumbnails
27 brand-collection landing pages — hero responsive srcset
Square aspect-ratio + object-fit:cover on Discover / Featured cards
PDP thumbnail wrapper height pre-reserved
Hover-state width/height redraw removed from .double__image
Image-fill sizes hint extended to 4 more card-context callers
WebP <picture> rolled out to remaining 3 snippets
Native lazy + alt added to cross-post-blogs, list-collections, section-collection-grid
Liquid post-processor adds width/height to blog-body images (parsed from URL)
image_url named-param migration across 46 files (208 calls modernised, May 2)

## Slide 8
Cumulative Layout Shift sprint
Field CLS p75 = 0.30 → 8 discrete fixes shipped Apr 29 → May 2
Fix | What it was | Effect
#pwa-modal display:none | Shop Sheriff PWA animated top keyframe | 2,126 events/7d eliminated
Shop Sheriff AMP uninstalled | App fully removed (osj closed May 2) | $1,188/yr saved
Judge.me medals visibility:hidden | Stops late hydration shift | Removed jdgm-hidden flicker
Cart freegifts 160 px reserve | + PDP price + recent-products | 1pi 49% poor cart-CLS fixed
PDP store-pickup 64 px reserve | + Flickity transition removed | e4a-α + e4a-β closed
Reamaze widget label position:fixed | Was injecting into normal flow | 14 events/7d eliminated
Klaviyo + LoyaltyLion overlays | position:fixed !important | e4a-γ + δ closed (May 2)
Blog body images aspect-ratio fallback | Width/height parsed from URL | Closed ex4
Header announcement min-height | + .points-box contain:layout | T9 closed
Validation: May 9 re-query (first clean 7-day post-fix CrUX window). If #MainContent stays at ~85 events/day → proceed to dependencies (cookie banner reserve, BOGOS injection-point fix).

## Slide 9
GTM cleanup + observability
Cleaner attribution, smaller container, real-shopper telemetry
GTM container cleanup
OAuth 2.0 desktop client provisioned in hairmnl-vertex GCP for autonomous GTM API access
Tier A + B + C cleanup executed: 28 browser-side pixel tags deleted
GA4 bot exclusion v139 — was 538k bot events / 14d on /pages/privacy-policy (49× homepage)
js_error renamed to hairmnl_js_error in v140 — eliminates Elevar collision; ~30k (not set) error events / 7d resolved
Smart SEO config integration for Offer schema (single source of truth)
CWV dashboard + RUM
Self-hosted CWV/PWI dashboard live on GitHub Pages (May 1)
Tabbed mobile/desktop view with CrUX integration
Per-metric tooltips with plain-English explanations + action guidance
web-vitals reporter shipped to GA4 — v4 attribution build with debug_target selector flowing real-shopper data
INP fixes (T5): consent-modal null guard, layout-thrash batching, dropped dev console.logs
Page 3 + Page 2 Table 3 finalisation still open (issue 24q)

## Slide 10
Code health pass — May 2
Theme-check linter sweep + image filter modernisation + locale sync
1,554
offenses Apr 28
33
offenses May 2
−97.9%
All 33 remaining are intentionally deferred
(32 ImgWidthAndHeight queued for CLS sprint, 1 vendor)
Concretely fixed
img_url → image_url named params across 46 files (208 calls modernised, no perf regression)
5 locale files synced (de, es, fr, pt-BR, pt) — newsletter + accessibility keys
8 stub snippets created for broken template references
BSS render double-extension bug fixed (3 silent-failure renders)
noImage asset_url fix — image_url doesn't accept raw strings
Hardcoded /cart/add and /collections/all routes replaced with routes.* objects
Critical CSS audit (ax0, May 3) — penthouse confirmed 39 KB well-tuned; 3 duplicate rules removed + btn--outline property fix; 363 bytes saved
Snippet DRY-up (aoe, May 3) — product-grid-item-branded + subcollection merged (−193 lines); 4-line stub; 25+ callers unchanged; live smoke-test passed

## Slide 11
What we shipped — May 7-14 sprint
Phase 2 — 8 days, ~50 issues closed, 11 substantive commits
Desktop CLS p75 good rate 30.5% → 56.3% (+25.8 pp) — biggest field win
Mobile CLS p75 good rate 74.5% → 82.3% (+7.8 pp)
GA4 metric_rating fix (d00) — unknown bucket 50% → 5% in 24h, RUM signal now clean
49 dead snippet files deleted (BSS Lock + Solution + LTAP)
kt0 CSS containment rule codified (lint + Playwright smoke test + .opencode_hints)
Dashboard: desktop trend charts + 3-band CWV zones + PSI noise band

## Slide 12
CLS Phase 2 — desktop focus
Six fixes targeting desktop-only contributors the May 2 sprint did not touch
jvf — Cart-page quantity + price cell min-heights
p52 — Judge.me PDP review block (220 px) + collection preview badge (18 px)
dzi → hod — BOGOS free-gift container 80 → 160 → 240 px (heavy-promo carts)
38l — LimeSpot card image aspect-ratio + object-fit lock
ojx — Pro-blogger related-articles thumbnail dimensions (136 URLs)
z9y — PDP Judge.me preview badge + gallery zoom yield (884 URLs)
987 #1 — Blog article body iframe/video aspect-ratio (YouTube/Vimeo/Instagram)
7i0 — Announcement bar ticker height lock (font-FOUT inner shift)

## Slide 13
kt0 CSS containment rule — three layers of prevention
After two cart-drawer + Reamaze regressions in three days, this is now policy
Rule: contain:layout / transform / filter / etc. on a parent of any fixed/abs descendant breaks overlay positioning silently
Layer 1 — Lint: scripts/check-overlay-css.py runs in CI on every PR touching .liquid/.css/.scss
Layer 2 — Smoke: scripts/smoke-test-drawers.py (Playwright) verifies cart drawer + mobile nav + search + modals on draft before live push
Layer 3 — Process: CSS reservation parity hint — grep both css-overrides.liquid AND custom-theme.css before editing
Caught the May 13 hod fix shipping as a NO-OP (selector-specificity trap) — computed-style smoke test required for every CSS reservation now

## Slide 14
GTM observability + third-party app rationalization
Real-shopper RUM data is now clean for the first time
d00 — gtag double-fire fix: metric_rating unknown 50-60% → 2-6% in 24h (LCP/CLS/INP/FCP/TTFB all clean)
vux — Reverted a GTM v141 instrumentation regression
t4m + 4r8 + miy — Three GTM tags with orphan trigger IDs repaired (Klaviyo, Conversion Linker, TrafficGuard)
BSS B2B Lock + Solution + LTAP uninstalled — 49 dead snippets removed, 2 dead fetch() calls per PDP eliminated
BookThatApp + VisualQuizBuilder uninstalled — 60-line createElement guard + 2 app block refs removed
Customer Portal preserved — gated to backbar-approved customers, zero guest perf cost (Decision 4 narrower now)

## Slide 15
Decisions pending
Five decisions ready for sign-off — ordered by ROI

## Slide 16
Decision 1 — LimeSpot 4 admin tweaks
HIGHEST ROI · free · ~30 min in LimeSpot admin · 2–5% AOV uplift
Recommendation: approve immediately. This is the most leveraged item on the roadmap.
1
Enable cart-page widget
Cart has zero LimeSpot widgets today. Single biggest miss. Industry benchmark: 2–5% AOV uplift in beauty/personal-care.
2
Reduce PDP product limit
PDP shows 18 + 20 = 38 products. Cut to 6–8 per widget. Above 8, choice paralysis kicks in (Baymard, NN/g).
3
Re-place PDP widgets
Widgets stack at 32–38% scroll. Move "Frequently Bought Together" right under Add-to-Cart, "You May Also Like" below description + reviews.
4
Add homepage widget
Homepage has zero widgets. Add a "Trending" or "Bestsellers" widget. Lower priority than #1–3 but standard.

## Slide 17
Decision 2 — Approve Vertex AI cutover plan
HIGH ROI · in-principle approval unlocks Phase 3 · $3,000–4,200/yr saved
Foundation + 4 widget slots already built. Need approval-in-principle so Phase 3 can move when team is satisfied with quality.
Build progress (separate session)
PR-1 universal foundation (CSS + shared snippets) ✓
PR-2 Cart-page FBT above checkout footer ✓
PR-3 Cart-drawer FBT below line items ✓
PR-4 PDP "You may also like" below description ✓
PR-5 Home RFY (model-gated) ✓
PR-6 Slot 3 home RFY section ✓
Round 1–3 team feedback applied (header pin, drawer nav, cart inline ADD, font inheritance)
Phase 1 catalog sync — next
Phase 2 event tracking pipeline — after Phase 1
Phase 3 cutover with 14-day monitor — gated on this decision
Cutover safety
Disable LimeSpot widgets in admin (kept installed for instant rollback)
Vertex widgets launch in same positions — Home, PDP, Cart, Cart Drawer
RPV / AOV / CVR / mobile blocking time monitored daily
If anything regresses → re-enable LimeSpot widgets (same minute)
After 14 clean days → uninstall LimeSpot, savings begin
Tradeoffs: Google Cloud as a vendor; less per-user personalisation than LimeSpot top tier

## Slide 18
Decision 3 — Admin batch (4 items)
MEDIUM ROI · ZERO RISK · all admin-only · ship as one approval
Recommendation: approve as single batch. No theme code change required for any of these.
Item | Owner | What it does
Snapchat Pixel removal (issue bvs) | Marketing | Custom Pixel / app embed / GTM. Removes one third-party script confirmed unused.
URL Redirect cleanup (issue 3q4) | Web team | Stale rule davines-momo-shampoo → / identified. Audit redirects with target=/. Likely 14–28 stale rules of 1,382 products.
Judge.me Lite mode (issue ebh) | Web team | Enable Lite mode, reduce reviews-per-page to 5–10, disable widgets not in active use.
Verify Subscribe It / Treedify / Hextom CTB (issue ijh) | Web team | Check Apps. If uninstalled, web team removes related theme code. Subscribe It is biggest at ~54 KB.

## Slide 19
Decision 4 — BSS B2B Customer Portal full uninstall
MEDIUM ROI · founder-only call · no perf urgency
JS already gated to logged-in pro accounts (~185 KB saved per guest pageload). The question is purely about whether the B2B portal still adds value.
KEEP
B2B portal flow continues to work for backbar-approved customers
No customer-facing change
Theme already optimised — JS gated to pro logins only
Risk: continued vendor coupling for niche feature
UNINSTALL
Simpler theme footprint
One fewer vendor on the stack
Minor follow-on cleanup of admin assets and dead snippets
Need to confirm: backbar-approved flow not actively used by current customers

## Slide 20
Decision 5 — Dual sale-label decision
LOW URGENCY · parked to Jun 1 · no action today
Recommendation: no action needed today. Issue spz parked until 2026-06-01. Revisit when bandwidth allows.
Background
New server-side product-labels system is built but disabled
Old .product__badge--custom system is sole sale-display path — stable
Code preserved for both — easy to flip
Bug already prevented in current code (no duplicate labels visible to shoppers)
Long-term recommendation
Migrate to new auto-computed system
Single source of truth for sale state
Less admin work for marketing / merchandising
Decision parked because shipped solution is stable; team can revisit when bandwidth allows

## Slide 21
Forward plan
Next 30 days · sequencing prioritises sign-off-pending and CrUX-validation-blocking work

## Slide 22
Next 30 days
May 6 → Jun 9
Week | Work | Owner
May 6 → 12 | Apply LimeSpot 4 admin tweaks (Decision 1) · Snapchat Pixel removal · URL Redirect audit · Judge.me Lite mode · verify ijh app statuses · e4a CLS field re-query May 9 | Founders + Marketing + Web team
May 13 → 19 | CLS dependencies (cookie banner reserve, BOGOS injection-point fix) if e4a re-query confirms #MainContent unchanged · Elevar /a/elevar 2.6 sec investigation · cart INP investigation completion (gjv) | Web team
May 20 → 26 | Vertex Phase 1 — catalog sync (Cloud Function pushing Shopify products + brand metadata + per-brand profit margins to Vertex daily and on product-change webhooks) | Web team (separate session)
May 27 → Jun 2 | Vertex Phase 2 — event tracking pipeline (page views, add-to-carts, purchases) sent to Vertex in real time. CrUX field 28-day window starts reflecting May-1 wins ~May 26 | Web team
Jun 3 → Jun 9 | Vertex Phase 3 — cutover with 14-day monitor. Decision-2 sign-off is gating. Daily monitoring of RPV / AOV / mobile blocking time. Instant rollback path live. | Founders sign-off + Web team

## Slide 23
QA watch items — recurring-risk bugs
For the web team to keep checking · 12 patterns
1
Draft / live theme drift — Pipeline 6.1.3 has no OS 2.0 auto-sync
2
Shopify CLI bulk push silently skips files (~50% on 134-file pushes)
3
Judge.me metafield format change — static stars depend on data-average-rating parse
4
Klaviyo popup hijacking LCP — watch for popup wrapper as LCP element
5
Lazysizes drift — class="lazyload" + data-src patterns invisible after lazysizes purge
6
OS 2.0 admin section drift — templates/*.json + settings_data.json admin-managed
7
Dual sale-label visual (spz) — flip risks duplicate visual return
8
CDN cache warming after live pushes — first 30–60 min window unreliable
9
PSI single-run variance — ±5–10 score / 5–10s LCP swings
10
GTM v140 hairmnl_js_error — revert risks Elevar collision
11
GA4 bot contamination — new GA4 triggers must inherit bot-exclusion blocking rule
12
BSS render double-extension — May-2 fix verified; no TBT regression

## Slide 24
Items off the table
Considered and ruled out — recorded so we don't re-litigate
Service Worker / PWA build — not feasible on this stack (likely conflict with Shop Sheriff PWA app and Shopify-side restrictions)
Re-uploading Kérastase collection images at higher resolution — not possible (brand assets managed by L'Oréal/Kérastase). CSS workaround (square aspect-ratio, image-cover) is the permanent fix
LimeSpot account-manager strategy review — not relevant given we're replacing the app
Migrating off Reamaze (customer support) — explicitly retained per founder decision; not in scope
Migrating off Judge.me to a different review app — theme-side optimisation already shipped; admin defer is the next path (handled by Decision 3)

## Slide 25
Projects in development
Bigger builds — separate sessions, multi-week timelines
These are tracked here for visibility but do not require this week's sign-off

## Slide 26
Vertex AI rec engine — 60-to-90 day build
Major project · separate Claude Code session · phase table below
Phase | Deliverable | Duration | Status
Setup | Provision GCP project · enable Vertex AI Search for Commerce · service accounts · billing alerts · confirm $600 free credit applied | Week 1 | Done
Foundation | PR-1 universal foundation: shared CSS + snippets · vrec-slot markup convention | Week 1 | Done
Widgets | PR-2 → PR-6: Cart-page FBT + Cart-drawer FBT + PDP YMAL + Home RFY · 3 rounds team review applied | Week 2–3 | Done
Catalog sync | Cloud Function pushes Shopify products + brand metadata + per-brand profit margins to Vertex AI catalog daily and on product-change webhooks | Week 4 | Next
Event tracking | Send shopper events (page views, add-to-cart, purchase) to Vertex in real time via thin theme-side tracking layer; defer all analytics scripts | Week 5 | Pending
Cutover + monitor | Disable LimeSpot widgets in admin (don't uninstall). Launch Vertex widgets in same positions. Monitor RPV/AOV/CVR/mobile blocking time daily for 14 days. Instant rollback path live. | Weeks 6–7 | Gated on Decision 2
Cleanup | After 14 clean days, uninstall LimeSpot. Capture $403/mo savings. | End week 7 | Pending

## Slide 27
Vertex AI build — performance non-negotiables
Written into the build prompt so we don't end up with a faster engine that's also slow
Recommendations render server-side in Liquid — not via JavaScript hydration
Vertex predict API call latency budget: under 100 ms at p95 — achieved via caching (precomputed metafields, edge cache, or Cloud Function proxy cache)
Multi-widget pages batch their predict requests into one call
Catalog and event sync never run on the request path (cron-based, async)
Profit-margin re-rank happens in Liquid: score × (1 + brand_margin_pct/100)
Mobile blocking time after launch must be lower than the LimeSpot baseline

## Slide 28
Other projects in development
Multi-day builds · parked or scheduled later
Project | Estimated effort | Status | Why parked
Phase 0 CRO data layer (issue l55) | Multi-week umbrella | Proposal documented | Foundational; needs Clarity + PostHog + GrowthBook + BigQuery + consent gate
Tree-shake vendor.js (issue yzk) | 1–2 days | Blocked | Needs build-pipeline access (Rellax/axios/ellipsis baggage)
jQuery removal (issue j0g) | Multi-day, high risk | Parked | Needs comprehensive QA across all templates + vendor snippets
STKY ATC custom replacement (issue r8r) | 3–4 hours | Parked | $300/yr saved — low priority vs higher-leverage work
BOGOS replacement custom logic (issue ur0) | 1 day | Parked | $420/yr saved — low priority
Snippet DRY-up (issue aoe) | Half-day | Pending | Consolidate 3 product-grid-item variants (~600 lines duplicated)
Critical-CSS audit + regen (issue ax0) | Half-day | Pending | ~40 KB inline contains 37 Swiper + 10 Flickity selectors, some duplicates
Custom-theme.js layout-thrash audit (issue 3sr) | Half-day | Deferred | No sourcemaps available — investigation cost high

## Slide 29
Glossary
For marketing, content, and founders
Performance
LCP — biggest visible thing appears. Goal: <2.5 s mobile.
INP — page reaction time on tap. Goal: <200 ms.
CLS — how much things jump around. Goal: <0.1.
TBT — page frozen by JS during load (lab).
FCP — first thing visible. Goal: <1.8 s.
TTFB — first byte of HTML. Goal: <800 ms.
CrUX — Google's real-shopper 28-day field data.
PSI / Lighthouse — Google's perf measurement tool.
Apps & vendors
LimeSpot — recs engine, $403/mo, being replaced.
Vertex AI — Google's recs engine, ~$50–150/mo.
Judge.me — review collection/display, $15/mo.
BSS B2B Portal — wholesale/pro features.
Klaviyo — email + popup.
Shop Sheriff AMP — uninstalled May 2.
LoyaltyLion — loyalty program.
Reamaze — customer support, retained.
GTM — tag container (v140).
Elevar — server-side conversion API.
Business / metrics
AOV — Average Order Value.
RPV — Revenue Per Visitor.
GMV — Gross Merchandise Value.
CTR — Click-Through Rate.
CVR — Conversion Rate.
GMC — Google Merchant Center.
GSC — Google Search Console.

## Slide 30
Summary asks — this week
Five decisions, ranked by ROI
1
Apply LimeSpot 4 admin tweaks — PENDING [fw8]
Free · 30 min · 2–5% AOV uplift
HIGHEST ROI
2
Approve Vertex cutover plan in principle — PENDING [oyw]
$3,000–4,200/yr saved · build is ready
HIGH ROI
3
Admin batch (4 items) — PENDING [bvs, 3q4, ebh, ijh]
URL Redirect · Judge.me Lite · ijh app verify
MEDIUM · ZERO RISK
4
Decide BSS B2B Customer Portal uninstall — PENDING [bjk, founder]
Founder-only · no perf urgency
MEDIUM · FOUNDER ONLY
5
Dual sale-label decision
Parked to Jun 1 · no action today
LOW URGENCY

## Slide 31
Questions?
Maintained by Claude Code · in collaboration with HairMNL
Updated May 14, 2026