## Slide 1
HAIR MNL
Engineering Brief
Replacing Appikon
Back in Stock
Feasibility & Recommendation
HairMNL Engineering · May 2026

## Slide 2
What Appikon Does Today — and What It Costs
2 / 12
$14.99
/ month
+ per-SMS charges
~₱830/mo
Appikon Back in Stock
Appikon captures customer email/SMS when a PDP variant is sold out
Triggers a restock alert when inventory goes above zero — driving restock-alert revenue
No reporting: no top-SKU view, no revenue attribution in Appikon’s dashboard
The brief asks us to replace it with an in-house system using Klaviyo — our existing CRM
Goal: eliminate the monthly fee, centralize customer data, and gain a purchasing-team report

## Slide 3
Proposed Architecture: PDP → Klaviyo → Email (+ SMS TBD)
3 / 12
Sold-out
PDP
Shopify storefront
Notify
Modal
Email / phone capture
Klaviyo
BIS API
CORS-friendly, public
Klaviyo
Flow
Email + optional SMS
hairmnl-data
Dashboard
Reporting
Optional SMS bridge via Semaphore or Twilio (if approved by stakeholders)
✔ No new backend server needed — Klaviyo’s public BIS API is CORS-friendly and requires only a public key
✔ Re-uses existing Klaviyo account (already manages newsletters + transactional emails for HairMNL)
✔ hairmnl-data reporting dashboard pulls Klaviyo event data and joins Shopify orders for revenue attribution

## Slide 4
Build on What We Already Have
4 / 12
Advantages
Zero new backend infrastructure to host or maintain
Klaviyo already holds all customer profiles + consent data
Single source of truth: newsletters, transactional, and now back-in-stock
Eliminates Appikon’s $14.99/mo fee on Day 1
Faster to ship: no database, no webhook signing, no Remix/Express app to build and host
One Known Limitation
Klaviyo flows fire per-event — cannot guarantee “oldest subscriber first” when stock is ≤5 units
Mitigation: rate-limit the flow to max 5 sends/min (best-effort FIFO)
Acceptable at HairMNL’s current waitlist volumes
Called out honestly — not a blocker for MVP

## Slide 5
Klaviyo SMS Doesn’t Serve the Philippines
5 / 12
⚠ Klaviyo’s native SMS product does not support Philippine (+63) numbers — confirmed.
Our brief includes an Email / SMS toggle for the notification capture modal
The standard Klaviyo Email + SMS flow cannot be used out of the box for Philippine customers
Path A: ship email-only MVP now — add SMS later via a thin serverless bridge if and when approved
Path B/C: integrate a PH-capable SMS provider (Semaphore or Twilio) alongside Klaviyo today
Engineering has costed all three options — decision matrix on the next slide
Stakeholder decision required before the engineering phase begins

## Slide 6
Three Paths for SMS Alerts
6 / 12
Option | Approach | Cost / SMS | Integration | Time to Ship | Vendor Risk
A. Skip SMS | Email-only MVP; no SMS toggle | ₱0 | Trivial — Klaviyo native | Fastest | None
B. Semaphore (PH-local) | Serverless fn bridges Klaviyo flow → Semaphore | ~₱0.50 (~$0.009) | Medium — 1 serverless fn + account | +1–2 days | Low
C. Twilio Programmable SMS | Same bridge but via Twilio | ~₱2.80 (~$0.05) | Medium — Twilio account + PH sender-ID reg. | +3–5 days | Low
Engineering recommends Option A for MVP — ship fastest, zero ongoing cost, revisit SMS in v2 once email conversion baseline is established.

## Slide 7
What Engineering Has Already Scoped
7 / 12
Decision | Choice | Why
Where the tab appears | PDPs only — sold-out variant | No site-wide injection; lighter JS load; no impact on collection or home pages
Phone country picker | Philippines (+63) hardcoded | Simplest implementation; HairMNL is a PH-only store
Reporting surface | hairmnl-data dashboard (existing) | Reuses 4×/day GitHub Actions pipeline + Shopify orders cache for revenue attribution
Waitlist migration | Investigation sub-task (T6) | Plan ships either way; T6 checks whether Appikon provides a subscriber CSV export
Newsletter opt-in | Preserved via second Klaviyo call | Consent checkbox triggers a Klaviyo list-subscription API call alongside the BIS subscription

## Slide 8
Four Weeks to Full Replacement
8 / 12
Week 1
Week 2
Week 3
Week 4
Theme
(UI)
Deck &
Klaviyo config
Modal + CTA + JS module
Smoke test
Appikon cutover
Critical path — blocks reporting track until Klaviyo config lands
Reporting
(data)
Klaviyo BIS client + cache (T8a)
Attribution join (T8b)
Charts + dashboard (T9)
Runs in parallel with theme track after Klaviyo config lands
Critical path: ~12–15h engineering serial. 4-week calendar target per brief.

## Slide 9
What Does Each Option Actually Cost?
9 / 12
Scenario | Month 1 | Monthly Ongoing | 12-Month Total
Status quo: Keep Appikon | $14.99 + SMS | ~$20–25 (incl. SMS) | ~$240–300
A. Email only (recommended) | $0 | $0 | $0
B. Email + Semaphore SMS | $0 | ~$1.75/mo (200 SMS est.) | ~$21
C. Email + Twilio SMS | $0 | ~$10/mo (200 SMS est.) | ~$120
All three in-house options pay back engineering cost within Month 1 versus keeping Appikon.

## Slide 10
Known Risks and How We’re Handling Them
10 / 12
Risk | Likelihood | Impact | Mitigation
Klaviyo flow misconfiguration sends alerts for wrong variants | Medium | High | Staging QA + manual flow test before cutover
Appikon waitlist lost if no CSV export available | Medium | Medium | T6 investigation sub-task. Plan ships either way; future signups captured from launch
FIFO fairness not guaranteed when stock ≤5 units | Low | Low | Rate-limit step (5/min) = best-effort FIFO; acceptable at HairMNL’s volumes
Klaviyo BIS API rate limits on sudden restock surge | Low | Medium | Exponential backoff implemented; BIS subscriptions are low-frequency events
SMS bridge adds micro-service overhead (Options B/C only) | Medium | Low | Only added if stakeholders approve SMS; email-only MVP avoids this entirely

## Slide 11
Three Decisions Needed from Leadership
11 / 12
01
SMS Path
Which SMS option do we proceed with?
A. Skip SMS (email-only MVP)
B. Semaphore — PH-local, ~₱0.50/SMS
C. Twilio — global, ~₱2.80/SMS
Engineering recommends: Option A
02
Appikon CSV Export
Should engineering pursue a waitlist export from Appikon?
Engineering has drafted an email to Appikon support.
Low effort — recovers the existing subscriber list if Appikon provides a CSV.
Approval needed to send the enquiry
03
Proceed to Build?
Approved to begin the engineering phase?
Timeline: 4 weeks from approval.
Deliverable: Appikon uninstalled, $14.99/mo saved, restock alerts live in Klaviyo.
Approval unlocks all engineering tracks

## Slide 12
Appendix — Supporting Detail
12 / 12
A — Brief excerpt (§1 Goals)
“Replace Appikon Back in Stock ($14.99/mo + SMS) with a Klaviyo-native in-house solution capturing email/SMS on sold-out PDPs and triggering restock alerts when inventory > 0. Reporting: total waitlist count, top-5 SKUs, conversion rate + revenue attributed.”
B — Engineering ticket graph
hairmnl-theme epic (9 tickets): modal snippet, product-form CTA swap, JS module, kt0 lint guard, smoke test, Appikon migration investigation, cutover, optional SMS bridge
hairmnl-data epic (3 tickets): Klaviyo BIS client + JSONL cache (T8a), attribution join + RestockReport DTO (T8b), dashboard charts + KPI cards (T9)
Tracker: bd (Beads) — embedded Dolt database, per-repo
C — Files created / deleted at cutover
NEW: snippets/notify-when-available-modal.liquid, assets/notify-when-available.dev.js, assets/notify-when-available.js, src/hairmnl/analytics/restock.py
DELETE: assets/subscribe-it.js (Appikon embed — never imported in Liquid; removed from Shopify App Embeds panel)
MODIFIED: snippets/product-form.liquid, layout/theme.liquid, snippets/css-overrides.liquid, locales/en.default.json